## Cover Page
CAPE TOWN PROPERTY DEVELOPMENT PROCESS MODEL
This indicative development process model was created to assist in highlighting the exceptionally long development timeframes (and resultant costs) for all stakeholders in the property development industry, including developers, consultants and government, with the objective of identifying opportunities to reduce time and cost by consensus. Whilst the model can be used to assist in understanding the development processes, it is by no means accurate in its entirety, and therefore professional and official advice is recommended at all times.
The model is largely premised on the development process associated with a mixed-use building comprising 10 000m² of GLA. Not all of the authorisation processes illustrated in the model may be triggered by a development of this type; nevertheless, they have been included for the purposes of completeness. The Triggers for Authorisations sheet identifies the types of authorisations that may be triggered depending on the specific characteristics of the development project. This model is broadly based on the PROCSA (2017) stages.
| Version: |  | August 2020
Disclaimer:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
| Key: |  | Link to another sheet
No link
Timeframe not legislated
Legislated timeframe
"Back" button
Acronyms:
| BAR | Basic Assessment Report
| BCO | Building Control Officer
| DEADP | Department of Environmental Affairs and Development Planning
| EIA | Environmental Impact Assessment
| EIR | Environmental Impact Report
| HIA | Heritage Impact Assessment
| HWC | Heritage Western Cape
| I&AP | Interested and Affected Party
| LUMS | Land Use Management
| LUPA | Land Use Planning Act
| MPBL | Municipal Planning By-Law
| MPT | Municipal Planning Tribunal
| NEMA | National Environmental Management Act
| NID | Notification of Intent to Develop
| NHRA | National Heritage Resources Act
| PPP | Public Participation Process
| SR | Scoping Report
| WUL | Water Use Licence
Acknowledgements:
Alison Ahmad - A + Quantity Surveyors
Anine Trumpelmann - @Planning Town Planning
Bridget O'Donoghue - Bridget O'Donoghue Architect Heritage Specialist Environment
Cheryl Walters - City of Cape Town
Chris Steffen - Talani Quantity Surveyors
David Hellig - David Hellig & Abrahamse Professional Land Surveyors
Deon van Zyl - Alwyn Laubser & Associates
Doug Jeffrey - Doug Jeffrey Environmental Consultants
Jaco van der Westhuizen - City of Cape Town
Jedd Grimbeek - Mitchell du Plessis Associates
Karen Le Jeune - UCT Department of Construction Economics & Management
Lewin Rolls - CnDV
Mark Massyn - UCT Department of Construction Economics & Management
Mida Kirova - Nigel Burls & Associates
Robert McGaffin - Urban Real Estate Research Unit
Simmy Peerutin - Peerutin Architects
Simon Beamish - Sibane Planning and Development

## Overview of Development Process
INDICATIVE OVERVIEW OF CAPE TOWN'S PROPERTY DEVELOPMENT PROCESS
[6 empty] | Year 1 | [11 empty] | Year 2 | [12 empty] | Year 3 | [11 empty] | Year 4 | [10 empty] | Year 5 | [11 empty] | Year 6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
PROJECT PHASES ADAPTED FROM PROCSA (2017)
Approved development rights (EIA / HERITAGE / LUMS / Etc.)
Appointments / Initial Design Options / Prelim Viability
Concept and Viability Approved
Detailed design / Building Plan preparation
[30 empty] | 4. DOCUMENTATION & PROCUREMENT | [18 empty] | Approve Building Plan
[34 empty] | 4. DOCUMENTATION & PROCUREMENT | [16 empty] | Tender / Appoint Main Contractor
Permit Application & Approval (Dept of Labour / Demolition / NHBRC / Etc.)
4. DOCUMENTATION & PROCUREMENT
Practical Completion Certificate
Commence Construction
Occupancy Certificate
Comments:
1. | The esimated length of Stage 0 above allows for a scoping period of prospective projects and an approximate 30 month period to prepare documentation and secure necessary authorisations as per example 8 on sheet Summary Authorisation Processes.
STAGE 0: PROJECT INITIATION & DEVELOPMENT RIGHTS
STAGE 1: INCEPTION
STAGE 3: DESIGN DEVELOPMENT
STAGE 4: BUILDING PLAN APPROVAL
STAGE 5: CONSTRUCTION
STAGE 6: CLOSE-OUT
STAGE 2: CONCEPT & VIABILITY
STAGE 4: MAIN CONTRACTOR TENDER DOC's & PROCUREMENT
STAGE 4: BALANCE OF DOCUMENTATION AND PROCUREMENT
PERMITS
STAGE 5: OCCUPANCY CERTIFICATE

## STAGE 0
STAGE 0: PROJECT INITIATION
Description: |  | Establish the need, desirability and viabilty of undertaking a property development together with securing the appropriate land and rights to undertake such a development in accordance with the project initiation programme.
Duration: |  | 36 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Establish project need and desirability
Procure market research investigation to evaluate product and feasibility
Appoint consultants
Prepare first business case, budget and end user requirements
Identify and secure land
Obtain land development rights (Click here)
Facilitate and manage development masterplan
Identify project funding sources and requirements
Back to Overview
of Development Process

## STAGE 1
STAGE 1: INCEPTION
Description: |  | Establish client requirements and preferences, assess user needs and options, appointment of necessary consultants, establish the project brief including project objectives, priorities, constraints, assumptions, aspirations and strategies.
Duration: |  | 3 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Formalise project brief
Establish procurement policy for the project
Appoint additional consultants
Formulate baseline project viability
Develop income, marketing and/or operating strategy
Manage project funding sources requirements
Prepare project initiation programme
Back to Overview
of Development Process

## STAGE 2
STAGE 2: CONCEPT & VIABILITY
Description: |  | Prepare and finalise the project concept in accordance with the brief including the scope, scale, character, form, function and preliminary development programme and viability of the project.
Duration: |  | 30 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Instruct the implementation of further surveys, analyses, tests and investigations (eg. geotechnical)
Prepare project financial viability
Manage & co-ordinate project funding requirements
Manage & co-ordinate the implementation of the marketing strategy
Collate project concept and viability
Secure approval of project finance
Prepare development programme
Prepare preliminary documentation programme
Prepare indicative construction programme
Preliminary estimates of construction costs
Architectural concept design
Engineering concept designs
Landscaping concept design
General construction material and finishes
Site development plan
Landscape development plan
Approval by client to proceed to stage 3
Back to Overview
of Development Process

## STAGE 3
STAGE 3: DESIGN DEVELOPMENT
Description: |  | Develop the approved concept to finalise the design, outline specifications, cost plan, financial viability and documentaton programme for the project.
Duration: |  | 7 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Appoint additional consultants
Prepare design and documentation programme
Prepare design development drawings and outline specifications
Prepare rational fire design
Submit necessary engineering design documentation to local authority for approval
Detailed estimates of construction costs
Establish, monitor and manage cash flow requirement of the project
Monitor achievement of the financial viability
Manage project finance pre-conditions
Back to Overview
of Development Process

## STAGE 4
STAGE 4: DOCUMENTATION & PROCUREMENT
Description: |  | Prepare construction and procurement documentation, confirm and implement the procurement programme, strategies and procedures for the effective and timeous procurement of necessary resources for the execution of the project.
Duration: |  | 18 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Prepare the procurement programme
Prepare procurement documentation
Prepare project specific tender and contract conditions
Review and approve proposed tenderers for the project
Adjudicate tenders and quotations
Sign principal and direct contract appointments
Procure necessary insurances for the project
Update and review project financial viability
Procure and manage legal advice in relation to the project
Secure signed services agreements with local authorities
Submit atchitectural drawings to local authoity for approval
Prepare working drawings
Back to Overview
of Development Process

## STAGE 5
STAGE 5: CONSTRUCTION
Description: |  | Manage, administer and monitor the contracts and processes, including the preparation and co-ordination of the procedures and documentation to facilitate practical completion of the works.
Duration: |  | 18 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Manage project insurance requirements
Site handover to the contractor
Secure approval of Contractor's Health and Safety Plan and permit to commence work
Establish construction documentation issue process
Prepare and distribute construction documentation
Contractor to appoint sub-contractors
Prepare construction programme
Monitor performance of contractor against construction programme
Undertake end user and tenant installations
Prepare operations, leasing and sales schedule
Rational fire design report of compliance status for occupation including fire authority approval
Secure certificate of practical completion
Secure Occupation certificate
Back to Overview
of Development Process
Construction
Process
Flowchart

## STAGE 6
STAGE 6: CLOSE-OUT
Description: |  | Fulfil and complete the project close-out including the preparation of the necessary documentation to facilitate effective completion, handover and operation of the project.
Duration: |  | 4 months
Activities & Deliverables:
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Prepare works and final completion lists
Prepare operations and maintenance manuals
Prepare as-built drawings and documentation
Monitor rectification of defects during defects liability period
Procure facilities management resources
Review occupancy and income parameters for compliance with financial viability
Secure completion certificates
Back to Overview
of Development Process

## Triggers for Authorisation
|  | Triggers | Relevant Legislation
|  | • No approved building plans for intended development | National Building Regulations and Building Standards Act 103 of 1977. (NBR)
|  | • Change in land use rights from what is permitted in MPBL and Scheme • Deviation from permitted development parameters • Deviation from conditions applicable to land (title deed or other past approvals) • Subdivision of land | Municipal Planning By-Law (eg. City of Cape Town Municipal Planning By-Law 2015)
Relevant Municipal Zoning Scheme ( eg. Development Management Scheme in Cape Town)
Roads Ordinance No 19 of 1976
Roads and Ribbons Development Act 21 of 1940
Western Cape Land Use Planning Act 3 of 2014 (LUPA)
National Spatial Planning and Land Use Management Act 16 of 2013 (SPLUMA)
| Heritage | • Permits: Building older than 60 years, Provincial or National Heritage site, protected area, heritage objects, monument. | National Heritage Resources Heritage Act 25 of 1999. (NHRA)
• Various triggers for NID submission (S38)
|  | • NEMA Listing Notice 1 & 3 | National Environmental Management Act 107 of 1998 (NEMA)
|  | • NEMA Listing Notice 2 | Various other associated acts such as the National Water Act, Waste Management Act, Air Quality Act, Noise regulations
|  | • Agricultural land outside previous municipal boundaries | Subdivision of Agricultural Land Act 70 of 1970)
|  | • Transformation of cultivated land | Western Cape Land Use Planning Act 3 of 2014 (LUPA) (S 53 application)
|  | • Development near a watercourse | National Water Act 36 of 1998
Comments:
1. | A combination of processes may be triggered depending on the characteristics of the development project. They may run concurrently to an extent but may be constrained by dependencies between them.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Building Plans
Planning - MPBL
Heritage
Environmental - BAR
Environmental - EIA
Agricultural - SALA
Agricultural - LUPA
Water Use
Back to Stage 0
To Summary of Authorisation Processes
Back to Overview
of Development Process

## Building Plan Approval
BUILDING PLAN APPROVAL
| Years | [11 empty] | 1
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Comments:
1. | The construction process illustrated above does not account for any delays due to builders' holidays, weather, and design changes.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Submit building
plans
Application referred to LUMS for clearance
Scrutiny fee calculated and invoice generated
Invoice paid
Applicant amends drawings
5 days to issue clearance
Comments compiled by plans examiner
(5 days)
Circulation to departments
(5 days per department)
Plans examiner re-circulates drawings
(5 days)
Circulation to departments
(5 days per department)
Plans examiner makes recommendation to Building Control Officer
BCO assesses and makes recommendation to Section Head
Section Head issues final approval
Back to Triggers for Authorisation
Back to Overview
of Development Process

## Land Use Application
LAND USE AUTHORISATION i.t.o. MPBL
| Years | [11 empty] | 1 | [11 empty] | 2
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Prepare application and supporting documentation
Pre-application consultation with Local Authority
Submit Application
Request for additional information
Additional information provided
Comments/ objections sent to applicant
14 days
30 days public notification & circulation to departments
Case officer writes report of recommendation to MPT
20 days response to comments
Acceptance of application
MPT decision to approve / refuse
Decision letter to applicant
21 day appeal period
Planning department submits report to Appeal Committee
Appeal Committee decision
Final notification of decision
Back to Triggers for Authorisation
Back to Overview
of Development Process

## HIA
HERITAGE IMPACT ASSESSMENT PROCESS
| Years | [11 empty] | 1
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
OR
OR
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Submit Notification of Intent to Develop (NID)
HWC response to NID
14 days
HIA i.t.o. NHRA s38(3) and s38(8)
HIA i.t.o. NHRA s38(3)
Submit HIA to EAP for PPP
PPP
30 days
Finalise HIA with comment & response report
Submit to HWC for comment
Submit to DEADP
PPP
30 days
Finalise HIA with comment & response report
Submit to HWC
HWC Impact Assessment Committee
HWC ROD
Revise HIA
Resubmit to I&APs
30 days
Resubmit to HWC
HWC Impact Assessment Committee
HWC ROD
Back to Triggers for Authorisation
Back to Overview
of Development Process

## BAR
ENVIRONMENTAL BASIC ASSESSMENT
| Years | [11 empty] | 1 | [11 empty] | 2
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Identify requirement for BAR process - NEMA Listing Notice 1&3
Conduct specialist investigations; Basic Assessment Report; Conduct initial Public Participation
Submit Application Form to DEADP
DEADP acknowledge acceptance
Conduct public participation
Submit final BAR to DEADP
Grant/refuse environmental authorisation in full or in part
10 days
30 days for comment on BAR
BAR must be submitted 90 days from date of receipt of application or 140 days if significant changes made
DEADP acknowledge acceptance of FBAR
10 days
107 days
Notify applicant of decision
10 days
Applicant to notify I&APs of decision
14 days
Appeal
6 days
Back to Triggers for Authorisation
Back to Overview
of Development Process

## EIA
ENVIRONMENTAL IMPACT ASSESSMENT
| Years | [11 empty] | 1 | [11 empty] | 2 | [5 empty] | 3
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Identify requirement for EIA process - NEMA Listing Notice 2
Conduct specialist investigations; Draft Scoping Report (SR); Conduct initial Public Participation
Submit Application Form to DEADP
DEADP acknowledge acceptance
Conduct public participation
Submit final SR and plan of study for EIR to DEADP
10 days
30 days for comment on SR
SR must be submitted 44 days from receipt of application
DEADP acknowledge acceptance of SR
10 days
43 days
DEADP reject application
Refuse environmental authorisation
Accept SR and Plan of Study
Prepare Environmental Impact Report (EIR); Conduct specialist investigations; Conduct Public Participation
30 days for comment on EIR
Submit Final EIR to DEADP
Acknowledgement of Final EIR
10 days
Grant/refuse environmental authorisation in full or in part
107 days
Notify applicant of decision
5 days
Applicant to notify I&APs of decision
14 days
Appeal
6 days
Submit EIR 106 days from acceptance of scoping report or 156 days if significant changes made
Back to Triggers for Authorisation
Back to Overview
of Development Process

## SALA
APPLICATION FOR EXCLUSION FROM PROVISIONS OF THE SUBDIVISION OF AGRICULTURAL LAND ACT 70 OF 1970
| Years | [11 empty] | 1 | [11 empty] | 2 | [11 empty] | 3
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Prepare application and suporting documentation
Obtain comment from D:EA&DP
Submit Application to National Department of Agriulture
Step 4:
Case officer compiles report for consideration by the Committee
Step 5:
Decision made by Committee
Applicant may appeal the decision if no new information is available. Appeal decision is made by the Minister.
Step 1-3
(administrative)
Steps 6-8
(administrative)
In-principle letter to applicant
Planning approval sent to National Department of Agriculture
Planning approval sent to National Department of Agriculture
National Department of Agriculture follows 8-step process again before issuing final approval
Applicant may apply for a reconsideration of the decision if new information is avaiable. This follows the 8-step process.
Back to Triggers for Authorisation
Back to Overview
of Development Process

## LUPA s53 Applicaton
APPLICATION IN TERMS OF S53 OF LUPA
| Years | [11 empty] | 1 | [11 empty] | 2
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Prepare application and supporting documentation
Pre-application consultation with Provincial Authority
Submit Application
Comments/ objections sent to applicant
30 days public notification & circulation to departments
Case officer writes report of recommendation to the HOD & Minister
20 days response to comments
Decision
Appeal process
Preparation of advert
Back to Triggers for Authorisation
Back to Overview
of Development Process

## WUL
WATER USE LICENCE AUTHORISATION
| Years | [11 empty] | 1 | [11 empty] | 2
| Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Comments:
1. | This programme assumes no dependencies with other authorisation processes.
2. | This programme does not make provision for any recess periods over December / January for the decision making authority.
3. | Although most of the timeframes above are legislated, they are seldom adhered to in practice.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Pre-application enquiry
Authority acknowledges receipt of application
(10 days)
Submit application form
Applicant confirms arrangement for site inspection
(5 days)
Site inspection to determine requirements
(20 days)
Confirmation requirements for technical report
(5 days)
Compilation, consultation and submission technical report (105 days)
Accept/reject technical report
(5 days)
Assessment by the relevant authority (139 days)
Decision & communication to applicant
(5 days)
Appeal
Back to Triggers for Authorisation
Back to Overview
of Development Process

## Summary Authorisation Processes
INDICATIVE EXAMPLES OF COMBINATIONS OF AUTHORISATIONS THAT MAY BE REQUIRED FOR DEVELOPMENT PROJECTS
Submission
|  | Month 9 | Month 8 | Month 7 | Month 6 | Month 5 | Month 4 | Month 3 | Month 2 | Month 1 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22
1. | Building Plans | [8 empty] | Plans | bar: Month 1 to Month 3
2. | Planning | [6 empty] | TIA, SDP, services |  |  | Month 1: Submit Planning application
3. | Planning & HIA | [7 empty] | NID |  | Month 4: Submit final HIA report
[8 empty] | TIA, SDP, services |  |  | Month 1: Submit Planning application
4. | Planning & BAR (Basic) |  |  | Specialist studies, draft BAR |  |  | PP + Final BAR |  |  |  | Month 1: Submit final BAR
[5 empty] | Planning motivation +input in EIA | [5 empty] | Month 1: Submit Planning application
5. | Planning & Full Scoping & Assessment |  |  |  |  | Draft Scoping |  | PP + Final scoping report |  |  | Month 1: Approve scoping; Month 3: Specialist reports, PP, amend
[6 empty] | Planning motivation +input in EIA |  |  |  |  | Month 8: Submit Planning application (after PP process)
6. | Planning, EIA & Heritage Report |  |  | NID |  |  |  | Submit report (HWC comment)
| (Heritage is input into EA) |  |  | Specialist studies, draft BAR |  |  | PP + Final BAR |  |  |  | Month 1: Submit final BAR
[5 empty] | Planning motivation +input in EIA & Heritage report | [5 empty] | Month 1: Submit Planning application
7. | Planning, EIA, HIA & SALA
|  |  |  | NID |  |  |  | Submit report (HWC comment)
|  |  |  | Specialist studies, draft BAR |  |  | PP + Final BAR | bar: Month 1 to Month 10
[5 empty] | Planning motivation +input in EIA & Heritage report | [5 empty] | Month 1: Submit Planning application
Submit SALA application (unlegislated time frame)
8. | Planning, EIA & Hertiage with appeal
|  |  |  | NID |  |  |  | Submit report (HWC comment)
|  |  |  | Specialist studies, draft BAR |  |  | PP + Final BAR |  |  |  | Month 1: Submit final BAR; Month 6: Appeal (between 6 months and 12 months)
[5 empty] | Planning motivation +input in EIA & Heritage report | [5 empty] | Month 1: Submit Planning application; Month 14: Appeal (Between 5 and 9 months)
9. | Actual Example
| Planning & Heritage with appeals | [5 empty] | NID |  |  |  | Month 7: Submit final HIA report
[6 empty] | TIA, SDP, Eng services, Tree survey etc |  |  |  |  | Month 1: Submit; Month 2: Advertise; Month 5: respond; Month 6: more info; Month 7: respond; Month 17: Notify; Month 18: Appeal (waiting for decision)
| Key: | Pre-submission processes and timeframes
Post-submission processes and timeframes
Disclaimers:
1. | The presubmission period may vary depending on the complexity of the project.
2. | Timelines are based on legislated timeframes (where applicable) and experience (in instances where no time limit is imposed in the legislation).
3. | Timeframes related to planning are based on the provisions of the Cape Town Municipal Planning By-Law. Other Municipalities prescribe different timeframes.
4. | Controvercail applications and applications with technical impediments (eg bulk services unavailable) may take longer.
5. | If a party intervenes, it could further delay planning applications.
6. | Buidling plans for subdivisions take longer due to clearances.
7. | After receiving a planning, environmental or heritage approval, there may be conditions which require to be complied with prior to a building plan being able to be submitted (eg consolidations, where the new erf number must first be registered) or prior to building plan approval. Depending on the nature of the condition, this may mean building plans cannot be submitted immediately folllowing planning approval, which may therefore delay plan submission or approval.
8. | The above time line does not take "dead period" over December holidays into consideration.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Subdivision conditions
Registration of erven
Dead Period
Dead Period
Back to Triggers for Authorisation
Back to Overview
of Development Process

## Construction Process
CONSTRUCTION PROCESS
Years | [11 empty] | 1 | [11 empty] | 2
Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
NOTE: Construction period based on a 10 storey building of 10 000m² GLA
Comments:
1. | The above time line does not take "dead period" over December holidays into consideration.
This model presents a snapshot of the Cape Town property development process in time (March 2019). The processes and associated timeframes are subject to change with amendments to legislation and general practice. This model is indicative and for illustrative purposes only. Although every effort has been made to be as comprehensive as possible, is not intended for it to be a definitive or exhaustive reflection of the property development process, nor is it intended for use as a project management tool.
Pre-construction
phase
Excavation & Substructure
Site
establishment
External Structure
Internal Structure
Roof
External envelope
Ceilings & internal divisions
Internal services
Snagging
Furnishing & fitout
Site
handover
Back to Stage 5
Back to Overview
of Development Process